## Portfolio Tracker
Programme Portfolio – RAG Status Tracker
Bajaj Finserv ¦ CoE & Technology Project Management Office — Reporting period FY2026-27 Q1 ¦ As of 31 May 2026
Programme Code | Programme Name | Business Line | Executive Sponsor | PMO Lead | Delivery Partner | Stage Gate | Start Date | Baseline Go-Live | Forecast Go-Live | % Complete | Schedule RAG | Budget RAG | Scope RAG | Overall RAG | Open RAID | P1 Open | Budget (₹ Cr) | Actual (₹ Cr) | % Budget Used | Last Updated | Status Commentary
BFS-LND-001 | Core Lending Platform Migration – Phase 2 (Commercial & SME) | Lending | Priya Venkat | Pavan Deshpande | Pennant Technologies | G5 – Hypercare | 2025-08-01 | 2026-04-30 | 2026-06-15 | 88% | Amber | Amber | Green | Amber | 4 | 0 | 28.5 | 23.5 | 82.46% | 2026-05-30 | Commercial/SME ledger live; dual-run recon underway, hypercare defects trending down.
BFS-AI-002 | FinAI – Conversational AI for Sales (BFL 3.0) | Sales / Enterprise | Vivek Malhotra | Sneha Iyer | In-house + Nagarro | G3 – Build | 2025-11-01 | 2026-09-30 | 2026-09-30 | 45% | Green | Green | Green | Green | 2 | 0 | 11 | 4.4 | 40% | 2026-05-30 | On track; guardrail design for product-claim compliance in progress.
BFS-AI-003 | FinAI – Explainable AI for Risk & Underwriting | Risk | Meera Krishnan | Kavita Rao | In-house | G4 – Test/UAT | 2025-09-15 | 2026-07-31 | 2026-08-31 | 62% | Amber | Green | Amber | Amber | 3 | 1 | 7.5 | 4.5 | 60% | 2026-05-30 | Model interpretability for RCU sign-off is the gating item; latency tuning ongoing.
BFS-AI-004 | FinAI – Copilot/Autopilot in Operations & Service | Operations | Anil Saxena | Rohan Mehta | In-house + Nagarro | G3 – Build | 2026-01-10 | 2026-12-15 | 2026-12-15 | 30% | Green | Amber | Green | Amber | 1 | 0 | 8.5 | 2.4 | 28.24% | 2026-05-30 | Maker-checker controls for autopilot actions under definition.
BFS-CLD-005 | Oracle Cloud Infrastructure Migration – Wave 2 | Enterprise | Rajeev Khanna | Arjun Nair | Oracle | G3 – Build | 2025-10-01 | 2026-05-31 | 2026-08-31 | 55% | Red | Red | Amber | Red | 4 | 3 | 23.5 | 17.7 | 75.32% | 2026-05-30 | Slipped 3 months: network latency + Oracle SME ramp + cloud spend overrun. Escalated.
BFS-DCX-006 | Bajaj Finserv Super-App Re-platform | Digital | Sanjay Bhandari | Sneha Iyer | Nagarro | G3 – Build | 2025-12-01 | 2026-10-31 | 2026-11-30 | 40% | Amber | Amber | Amber | Amber | 3 | 0 | 12 | 5.8 | 48.33% | 2026-05-30 | Front-end pod under-staffed; low-end Android performance below benchmark.
BFS-CMP-007 | AML Uplift – Azentio Amlock Upgrade | Compliance | Meera Krishnan | Imran Sheikh | Azentio | G4 – Test/UAT | 2025-09-01 | 2026-06-30 | 2026-06-30 | 75% | Green | Green | Green | Green | 2 | 0 | 7 | 5.5 | 78.57% | 2026-05-30 | UAT progressing; false-positive tuning and FIU-IND format validation pending.
BFS-GRN-008 | Green Finance – Solar & EV Financing Onboarding | Lending | Priya Venkat | Kavita Rao | In-house | G2 – Planning | 2026-03-01 | 2026-11-30 | 2026-11-30 | 18% | Green | Green | Amber | Amber | 2 | 0 | 5 | 0.4 | 8% | 2026-05-30 | Planning phase; partner-API discovery for asset valuation underway.
BFS-DLO-009 | Digital Loan Origination System Upgrade | Lending | Priya Venkat | Pavan Deshpande | In-house + Pennant | G4 – Test/UAT | 2025-10-15 | 2026-07-15 | 2026-08-15 | 68% | Amber | Amber | Red | Red | 4 | 1 | 10 | 6.5 | 65% | 2026-05-30 | Scope creep (6 product variants) + RBI DLG KFS compliance gap; Pennant disbursal API pending.
BFS-OBS-010 | Observability Rollout – New Relic APM | Enterprise | Rajeev Khanna | Arjun Nair | New Relic | G5 – Hypercare | 2025-07-01 | 2026-03-31 | 2026-03-31 | 95% | Green | Green | Green | Green | 0 | 0 | 4 | 3.8 | 95% | 2026-05-30 | Live; SLO-based alerting adopted, alert-noise issue closed.
BFS-CX-011 | Adobe Experience Cloud – Campaign Personalisation | Marketing | Sanjay Bhandari | Rohan Mehta | Adobe | G3 – Build | 2025-11-15 | 2026-08-31 | 2026-09-30 | 50% | Amber | Green | Amber | Amber | 2 | 0 | 8.5 | 4.3 | 50.59% | 2026-05-30 | Depends on Customer 360 segments; interim use of existing CDP.
BFS-DAT-012 | Customer 360 Data Platform | Data | Vivek Malhotra | Imran Sheikh | In-house + Nagarro | G3 – Build | 2025-08-15 | 2026-06-30 | 2026-10-31 | 48% | Red | Red | Red | Red | 4 | 3 | 17.5 | 9.7 | 55.43% | 2026-05-30 | Golden-record match 82% vs 95%; ~22% over budget; key-person risk on data architect.
Illustrative training data — fictional figures and names built on publicly reported Bajaj Finserv transformation themes (Pennant pennApps migration, BFL 3.0 FinAI, OCI 2025, Customer 360). Not actual company data.

## RAID Log
RAID Log – Risks, Assumptions, Issues & Dependencies
Bajaj Finserv ¦ CoE & Technology Project Management Office — Reporting period FY2026-27 Q1 ¦ As of 31 May 2026
RAID ID | Programme Code | Type | Category | Description | Raised Date | Owner | Probability | Impact | Priority | Status | Target Resolution | Mitigation / Action | Last Reviewed
R-001 | BFS-LND-001 | Risk | Data | Reconciliation variance of 0.3% on commercial loan ledger during Phase 2 cutover | 2026-04-10 | Farah Khan | Medium | High | P2 | Mitigating | 2026-06-10 | Daily recon scripts + dual-run with legacy LMS for 2 cycles | 2026-05-28
R-002 | BFS-LND-001 | Dependency | Vendor | Pennant hypercare extension SOW required before legacy LMS decommission | 2026-04-22 | Pavan Deshpande | – | High | P2 | Open | 2026-06-05 | SOW under legal review; escalated to vendor management | 2026-05-30
R-003 | BFS-LND-001 | Issue | Technical | Batch EOD job runtime exceeds SLA window by ~40 min post-migration | 2026-05-12 | Sandeep Reddy | – | Medium | P3 | In Progress | 2026-06-12 | Query tuning + partition strategy with Pennant | 2026-05-29
R-004 | BFS-AI-003 | Risk | Regulatory | Explainable-AI interpretability not meeting RCU/audit threshold for adverse-action reasons | 2026-03-20 | Harish Bhat | High | High | P1 | Mitigating | 2026-07-15 | SHAP-based reason codes + model-risk sign-off with CRO office | 2026-05-27
R-005 | BFS-AI-003 | Assumption | Data | Assumes 24 months of clean bureau + behavioural data available for training | 2026-02-15 | Farah Khan | – | Medium | P3 | Open | 2026-06-30 | Data-quality assessment in progress | 2026-05-20
R-006 | BFS-CLD-005 | Issue | Technical | OCI network latency to on-prem core breaching 20ms target for synchronous calls | 2026-04-05 | George Mathew | – | High | P1 | In Progress | 2026-06-20 | FastConnect dedicated link + workload re-architecture | 2026-05-30
R-007 | BFS-CLD-005 | Risk | Vendor | Oracle implementation resource ramp behind plan; 3 of 8 SMEs unfilled | 2026-03-28 | Arjun Nair | High | High | P1 | Open | 2026-06-15 | Escalated to Oracle delivery exec; backfill from partner pool | 2026-05-29
R-008 | BFS-CLD-005 | Risk | Financial | Cloud consumption tracking ahead of budget; FinOps guardrails not yet enforced | 2026-04-18 | Neha Kulkarni | High | Medium | P2 | Mitigating | 2026-06-30 | Budget alerts + tagging policy + monthly FinOps review | 2026-05-26
R-009 | BFS-CLD-005 | Dependency | Security | InfoSec cloud security baseline sign-off pending before Wave 2 prod cutover | 2026-04-25 | Harish Bhat | – | High | P1 | Open | 2026-07-10 | Security review scheduled; CCM controls mapping underway | 2026-05-28
R-010 | BFS-DAT-012 | Issue | Data | Customer master golden-record match rate at 82% vs 95% target | 2026-04-02 | Farah Khan | – | High | P1 | In Progress | 2026-07-31 | Tuning match-merge rules + manual stewardship for top accounts | 2026-05-30
R-011 | BFS-DAT-012 | Risk | Resource | Single data-architect dependency creating key-person risk across DAT-012 and AI-003 | 2026-03-15 | Anuradha Kulkarni | High | High | P1 | Mitigating | 2026-06-30 | Onboard second architect; knowledge-transfer plan | 2026-05-25
R-012 | BFS-DAT-012 | Risk | Financial | Forecast at completion trending ~22% over budget due to extended data remediation | 2026-04-20 | Neha Kulkarni | High | High | P1 | Open | 2026-06-15 | Re-baseline + change request to steering committee | 2026-05-30
R-013 | BFS-DAT-012 | Dependency | Technical | Customer 360 depends on OCI Wave 2 landing zone (BFS-CLD-005) | 2026-03-30 | Imran Sheikh | – | High | P2 | Open | 2026-07-15 | Joint milestone tracking with CLD-005; contingency on-prem staging | 2026-05-29
R-014 | BFS-DLO-009 | Issue | Scope | Scope creep: 6 additional product variants requested by business post-baseline | 2026-04-08 | Pavan Deshpande | – | High | P2 | In Progress | 2026-06-20 | Change control; defer 3 variants to Phase 2 | 2026-05-28
R-015 | BFS-DLO-009 | Risk | Regulatory | RBI Digital Lending Guidelines (DLG) KFS auto-generation not fully compliant in build | 2026-03-25 | Harish Bhat | Medium | High | P1 | Mitigating | 2026-07-01 | Compliance walkthrough + KFS template rework | 2026-05-27
R-016 | BFS-DLO-009 | Dependency | Vendor | Pennant instant-disbursal API pending; blocks end-to-end UAT | 2026-04-15 | Kavita Rao | – | High | P2 | Open | 2026-06-25 | Vendor commitment for sandbox by mid-June | 2026-05-30
R-017 | BFS-DCX-006 | Risk | Technical | Super-app performance on low-end Android devices below benchmark | 2026-04-12 | Sandeep Reddy | Medium | Medium | P3 | Open | 2026-07-15 | Performance profiling + lazy-loading + APK size reduction | 2026-05-26
R-018 | BFS-DCX-006 | Issue | Resource | Nagarro front-end pod under-staffed by 2 React engineers | 2026-04-19 | Sneha Iyer | – | Medium | P3 | In Progress | 2026-06-30 | Vendor backfill commitment; interim load balancing | 2026-05-29
R-019 | BFS-DCX-006 | Assumption | Scope | Assumes existing API gateway can handle 2x peak transaction volume | 2026-03-10 | Sandeep Reddy | – | Medium | P3 | Open | 2026-06-30 | Load test planned in UAT | 2026-05-22
R-020 | BFS-AI-002 | Risk | Regulatory | Conversational AI responses need guardrails for mis-selling / product claims | 2026-04-01 | Harish Bhat | Medium | High | P2 | Mitigating | 2026-07-31 | Guardrail prompts + human-in-loop review + DPDP alignment | 2026-05-28
R-021 | BFS-AI-002 | Assumption | Data | Assumes consent captured to use chat transcripts in fine-tuning (DPDP) | 2026-03-18 | Deepa Menon | – | High | P2 | Open | 2026-06-30 | Legal review of consent flows | 2026-05-24
R-022 | BFS-AI-004 | Risk | Scope | Autopilot scope for high-risk ops actions needs maker-checker controls | 2026-04-14 | Rohan Mehta | Medium | High | P2 | Open | 2026-07-31 | Define control matrix; restrict autopilot to low-risk actions in P1 | 2026-05-27
R-023 | BFS-CMP-007 | Issue | Technical | Amlock upgrade false-positive alert rate up ~15% in UAT | 2026-04-22 | Imran Sheikh | – | Medium | P3 | In Progress | 2026-06-20 | Threshold tuning with Azentio + scenario calibration | 2026-05-29
R-024 | BFS-CMP-007 | Dependency | Regulatory | FIU-IND reporting format validation sign-off needed before go-live | 2026-04-10 | Harish Bhat | – | High | P2 | Open | 2026-06-25 | Compliance validation scheduled | 2026-05-28
R-025 | BFS-GRN-008 | Assumption | Scope | Assumes solar/EV partner APIs available for asset valuation at onboarding | 2026-03-20 | Kavita Rao | – | Medium | P3 | Open | 2026-08-31 | Partner-API discovery in planning phase | 2026-05-20
R-026 | BFS-GRN-008 | Risk | Resource | Shared BA capacity across GRN-008 and DLO-009 may delay requirements sign-off | 2026-04-05 | Deepa Menon | Medium | Medium | P3 | Open | 2026-07-15 | Sequence requirements; add contractor BA | 2026-05-25
R-027 | BFS-LND-001 | Risk | Resource | Hypercare team fatigue; extended on-call since Phase 1 | 2026-05-02 | Pavan Deshpande | Medium | Medium | P3 | Open | 2026-06-15 | Rotation plan + ramp-down as defects stabilise | 2026-05-30
R-028 | BFS-OBS-010 | Issue | Technical | Alert noise during initial APM rollout causing on-call fatigue | 2026-03-15 | Arjun Nair | – | Low | P4 | Closed | 2026-04-30 | Alert tuning completed; SLO-based alerting adopted | 2026-04-28
R-029 | BFS-CX-011 | Risk | Data | Segmentation data freshness lag impacting campaign personalisation accuracy | 2026-04-16 | Rohan Mehta | Medium | Medium | P3 | Open | 2026-07-15 | Near-real-time feed from Customer 360 once available | 2026-05-27
R-030 | BFS-CX-011 | Dependency | Technical | Depends on Customer 360 (DAT-012) for unified customer segments | 2026-04-16 | Imran Sheikh | – | Medium | P3 | Open | 2026-08-31 | Interim use of existing CDP segments | 2026-05-27
R-031 | BFS-AI-003 | Issue | Technical | Model latency ~800ms exceeds 300ms target for real-time underwriting | 2026-05-05 | Sandeep Reddy | – | High | P2 | In Progress | 2026-06-30 | Model optimisation + feature-store caching | 2026-05-30
R-032 | BFS-DLO-009 | Risk | Financial | Forecast at completion ~8% over budget due to scope additions | 2026-04-28 | Neha Kulkarni | Medium | Medium | P2 | Open | 2026-06-30 | Change control + budget re-forecast | 2026-05-29

## Resourcing
Resource & Capacity Allocation
Bajaj Finserv ¦ CoE & Technology Project Management Office — Reporting period FY2026-27 Q1 ¦ As of 31 May 2026
Resource Name | Role | Band | Base Location | Employment | Vendor | Programme Code | Programme Name | Allocation % | Total Alloc % (person) | Period Start | Period End
Anuradha Kulkarni | PMO Head | M5 | Pune | Permanent | – | BFS-DAT-012 | Customer 360 Data Platform | 25% | 90% | 2026-04-01 | 2026-09-30
Anuradha Kulkarni | PMO Head | M5 | Pune | Permanent | – | BFS-CLD-005 | Oracle Cloud Infrastructure Migration – Wave 2 | 25% | 90% | 2026-04-01 | 2026-09-30
Anuradha Kulkarni | PMO Head | M5 | Pune | Permanent | – | BFS-LND-001 | Core Lending Platform Migration – Phase 2 (Commercial & SME) | 20% | 90% | 2026-04-01 | 2026-09-30
Anuradha Kulkarni | PMO Head | M5 | Pune | Permanent | – | BFS-AI-003 | FinAI – Explainable AI for Risk & Underwriting | 20% | 90% | 2026-04-01 | 2026-09-30
Pavan Deshpande | Senior Project Manager | M3 | Pune | Permanent | – | BFS-LND-001 | Core Lending Platform Migration – Phase 2 (Commercial & SME) | 60% | 110% | 2026-04-01 | 2026-09-30
Pavan Deshpande | Senior Project Manager | M3 | Pune | Permanent | – | BFS-DLO-009 | Digital Loan Origination System Upgrade | 50% | 110% | 2026-04-01 | 2026-09-30
Sneha Iyer | Senior Project Manager | M3 | Pune | Permanent | – | BFS-AI-002 | FinAI – Conversational AI for Sales (BFL 3.0) | 50% | 110% | 2026-04-01 | 2026-09-30
Sneha Iyer | Senior Project Manager | M3 | Pune | Permanent | – | BFS-DCX-006 | Bajaj Finserv Super-App Re-platform | 60% | 110% | 2026-04-01 | 2026-09-30
Kavita Rao | Project Manager | M2 | Pune | Permanent | – | BFS-AI-003 | FinAI – Explainable AI for Risk & Underwriting | 50% | 110% | 2026-04-01 | 2026-09-30
Kavita Rao | Project Manager | M2 | Pune | Permanent | – | BFS-GRN-008 | Green Finance – Solar & EV Financing Onboarding | 30% | 110% | 2026-04-01 | 2026-09-30
Kavita Rao | Project Manager | M2 | Pune | Permanent | – | BFS-DLO-009 | Digital Loan Origination System Upgrade | 30% | 110% | 2026-04-01 | 2026-09-30
Rohan Mehta | Project Manager | M2 | Mumbai | Permanent | – | BFS-AI-004 | FinAI – Copilot/Autopilot in Operations & Service | 50% | 100% | 2026-04-01 | 2026-09-30
Rohan Mehta | Project Manager | M2 | Mumbai | Permanent | – | BFS-CX-011 | Adobe Experience Cloud – Campaign Personalisation | 50% | 100% | 2026-04-01 | 2026-09-30
Arjun Nair | Project Manager | M2 | Pune | Permanent | – | BFS-CLD-005 | Oracle Cloud Infrastructure Migration – Wave 2 | 60% | 80% | 2026-04-01 | 2026-09-30
Arjun Nair | Project Manager | M2 | Pune | Permanent | – | BFS-OBS-010 | Observability Rollout – New Relic APM | 20% | 80% | 2026-04-01 | 2026-09-30
Imran Sheikh | Project Manager | M2 | Bengaluru | Permanent | – | BFS-CMP-007 | AML Uplift – Azentio Amlock Upgrade | 40% | 90% | 2026-04-01 | 2026-09-30
Imran Sheikh | Project Manager | M2 | Bengaluru | Permanent | – | BFS-DAT-012 | Customer 360 Data Platform | 50% | 90% | 2026-04-01 | 2026-09-30
Deepa Menon | Business Analyst Lead | M2 | Pune | Permanent | – | BFS-AI-002 | FinAI – Conversational AI for Sales (BFL 3.0) | 30% | 100% | 2026-04-01 | 2026-09-30
Deepa Menon | Business Analyst Lead | M2 | Pune | Permanent | – | BFS-GRN-008 | Green Finance – Solar & EV Financing Onboarding | 30% | 100% | 2026-04-01 | 2026-09-30
Deepa Menon | Business Analyst Lead | M2 | Pune | Permanent | – | BFS-DLO-009 | Digital Loan Origination System Upgrade | 40% | 100% | 2026-04-01 | 2026-09-30
Vikram Joshi | Business Analyst | M1 | Pune | Permanent | – | BFS-LND-001 | Core Lending Platform Migration – Phase 2 (Commercial & SME) | 50% | 100% | 2026-04-01 | 2026-09-30
Vikram Joshi | Business Analyst | M1 | Pune | Permanent | – | BFS-DLO-009 | Digital Loan Origination System Upgrade | 50% | 100% | 2026-04-01 | 2026-09-30
Pooja Shah | Business Analyst | M1 | Mumbai | Permanent | – | BFS-DCX-006 | Bajaj Finserv Super-App Re-platform | 50% | 100% | 2026-04-01 | 2026-09-30
Pooja Shah | Business Analyst | M1 | Mumbai | Permanent | – | BFS-CX-011 | Adobe Experience Cloud – Campaign Personalisation | 50% | 100% | 2026-04-01 | 2026-09-30
Nilesh Patil | PMO Coordinator | M1 | Pune | Permanent | – | BFS-CLD-005 | Oracle Cloud Infrastructure Migration – Wave 2 | 50% | 100% | 2026-04-01 | 2026-09-30
Nilesh Patil | PMO Coordinator | M1 | Pune | Permanent | – | BFS-DAT-012 | Customer 360 Data Platform | 50% | 100% | 2026-04-01 | 2026-09-30
Ritu Agarwal | PMO Coordinator | M1 | Pune | Permanent | – | BFS-LND-001 | Core Lending Platform Migration – Phase 2 (Commercial & SME) | 40% | 100% | 2026-04-01 | 2026-09-30
Ritu Agarwal | PMO Coordinator | M1 | Pune | Permanent | – | BFS-AI-003 | FinAI – Explainable AI for Risk & Underwriting | 30% | 100% | 2026-04-01 | 2026-09-30
Ritu Agarwal | PMO Coordinator | M1 | Pune | Permanent | – | BFS-CMP-007 | AML Uplift – Azentio Amlock Upgrade | 30% | 100% | 2026-04-01 | 2026-09-30
Sandeep Reddy | Solution Architect | M3 | Bengaluru | Permanent | – | BFS-DCX-006 | Bajaj Finserv Super-App Re-platform | 40% | 120% | 2026-04-01 | 2026-09-30
Sandeep Reddy | Solution Architect | M3 | Bengaluru | Permanent | – | BFS-AI-003 | FinAI – Explainable AI for Risk & Underwriting | 40% | 120% | 2026-04-01 | 2026-09-30
Sandeep Reddy | Solution Architect | M3 | Bengaluru | Permanent | – | BFS-DLO-009 | Digital Loan Origination System Upgrade | 40% | 120% | 2026-04-01 | 2026-09-30
Farah Khan | Data Architect | M3 | Pune | Permanent | – | BFS-DAT-012 | Customer 360 Data Platform | 60% | 110% | 2026-04-01 | 2026-09-30
Farah Khan | Data Architect | M3 | Pune | Permanent | – | BFS-AI-003 | FinAI – Explainable AI for Risk & Underwriting | 30% | 110% | 2026-04-01 | 2026-09-30
Farah Khan | Data Architect | M3 | Pune | Permanent | – | BFS-LND-001 | Core Lending Platform Migration – Phase 2 (Commercial & SME) | 20% | 110% | 2026-04-01 | 2026-09-30
Karthik Subramanian | QA Lead | M2 | Bengaluru | Permanent | – | BFS-LND-001 | Core Lending Platform Migration – Phase 2 (Commercial & SME) | 30% | 100% | 2026-04-01 | 2026-09-30
Karthik Subramanian | QA Lead | M2 | Bengaluru | Permanent | – | BFS-CMP-007 | AML Uplift – Azentio Amlock Upgrade | 30% | 100% | 2026-04-01 | 2026-09-30
Karthik Subramanian | QA Lead | M2 | Bengaluru | Permanent | – | BFS-DLO-009 | Digital Loan Origination System Upgrade | 40% | 100% | 2026-04-01 | 2026-09-30
Megha Gupta | Scrum Master | M2 | Pune | Permanent | – | BFS-AI-002 | FinAI – Conversational AI for Sales (BFL 3.0) | 50% | 100% | 2026-04-01 | 2026-09-30
Megha Gupta | Scrum Master | M2 | Pune | Permanent | – | BFS-AI-004 | FinAI – Copilot/Autopilot in Operations & Service | 50% | 100% | 2026-04-01 | 2026-09-30
Aditya Verma | Scrum Master | M2 | Mumbai | Permanent | – | BFS-DCX-006 | Bajaj Finserv Super-App Re-platform | 50% | 100% | 2026-04-01 | 2026-09-30
Aditya Verma | Scrum Master | M2 | Mumbai | Permanent | – | BFS-CX-011 | Adobe Experience Cloud – Campaign Personalisation | 50% | 100% | 2026-04-01 | 2026-09-30
Tara D'Souza | Change & Comms Lead | M2 | Pune | Permanent | – | BFS-LND-001 | Core Lending Platform Migration – Phase 2 (Commercial & SME) | 20% | 80% | 2026-04-01 | 2026-09-30
Tara D'Souza | Change & Comms Lead | M2 | Pune | Permanent | – | BFS-DLO-009 | Digital Loan Origination System Upgrade | 20% | 80% | 2026-04-01 | 2026-09-30
Tara D'Souza | Change & Comms Lead | M2 | Pune | Permanent | – | BFS-DCX-006 | Bajaj Finserv Super-App Re-platform | 20% | 80% | 2026-04-01 | 2026-09-30
Tara D'Souza | Change & Comms Lead | M2 | Pune | Permanent | – | BFS-AI-002 | FinAI – Conversational AI for Sales (BFL 3.0) | 20% | 80% | 2026-04-01 | 2026-09-30
Harish Bhat | Risk & Compliance Liaison | M3 | Pune | Permanent | – | BFS-AI-003 | FinAI – Explainable AI for Risk & Underwriting | 25% | 100% | 2026-04-01 | 2026-09-30
Harish Bhat | Risk & Compliance Liaison | M3 | Pune | Permanent | – | BFS-DLO-009 | Digital Loan Origination System Upgrade | 25% | 100% | 2026-04-01 | 2026-09-30
Harish Bhat | Risk & Compliance Liaison | M3 | Pune | Permanent | – | BFS-CLD-005 | Oracle Cloud Infrastructure Migration – Wave 2 | 25% | 100% | 2026-04-01 | 2026-09-30
Harish Bhat | Risk & Compliance Liaison | M3 | Pune | Permanent | – | BFS-CMP-007 | AML Uplift – Azentio Amlock Upgrade | 25% | 100% | 2026-04-01 | 2026-09-30
Neha Kulkarni | Finance Controller (PMO) | M2 | Pune | Permanent | – | BFS-CLD-005 | Oracle Cloud Infrastructure Migration – Wave 2 | 30% | 80% | 2026-04-01 | 2026-09-30
Neha Kulkarni | Finance Controller (PMO) | M2 | Pune | Permanent | – | BFS-DAT-012 | Customer 360 Data Platform | 30% | 80% | 2026-04-01 | 2026-09-30
Neha Kulkarni | Finance Controller (PMO) | M2 | Pune | Permanent | – | BFS-DLO-009 | Digital Loan Origination System Upgrade | 20% | 80% | 2026-04-01 | 2026-09-30
Ramesh Iyengar | Delivery Lead | M3 | Hyderabad | Vendor | Pennant | BFS-LND-001 | Core Lending Platform Migration – Phase 2 (Commercial & SME) | 60% | 100% | 2026-04-01 | 2026-09-30
Ramesh Iyengar | Delivery Lead | M3 | Hyderabad | Vendor | Pennant | BFS-DLO-009 | Digital Loan Origination System Upgrade | 40% | 100% | 2026-04-01 | 2026-09-30
Lakshmi Narayan | QA Lead | M2 | Pune | Vendor | Nagarro | BFS-DCX-006 | Bajaj Finserv Super-App Re-platform | 50% | 100% | 2026-04-01 | 2026-09-30
Lakshmi Narayan | QA Lead | M2 | Pune | Vendor | Nagarro | BFS-AI-002 | FinAI – Conversational AI for Sales (BFL 3.0) | 30% | 100% | 2026-04-01 | 2026-09-30
Lakshmi Narayan | QA Lead | M2 | Pune | Vendor | Nagarro | BFS-DAT-012 | Customer 360 Data Platform | 20% | 100% | 2026-04-01 | 2026-09-30
George Mathew | Cloud Architect | M3 | Bengaluru | Vendor | Oracle | BFS-CLD-005 | Oracle Cloud Infrastructure Migration – Wave 2 | 100% | 100% | 2026-04-01 | 2026-09-30
Aakash Pillai | DevOps Engineer | M1 | Pune | Vendor | Nagarro | BFS-OBS-010 | Observability Rollout – New Relic APM | 40% | 100% | 2026-04-01 | 2026-09-30
Aakash Pillai | DevOps Engineer | M1 | Pune | Vendor | Nagarro | BFS-CLD-005 | Oracle Cloud Infrastructure Migration – Wave 2 | 60% | 100% | 2026-04-01 | 2026-09-30

## Budget vs Actuals
Budget vs Actuals – Programme & Vendor Spend (₹ Crore)
Bajaj Finserv ¦ CoE & Technology Project Management Office — Reporting period FY2026-27 Q1 ¦ As of 31 May 2026
Programme Code | Programme Name | Vendor / Partner | Capex / Opex | Cost Type | Budget FY26-27 (₹ Cr) | Committed PO (₹ Cr) | Actual to Date (₹ Cr) | Forecast at Completion (₹ Cr) | Variance (₹ Cr) | Variance % | PO Number
BFS-LND-001 | Core Lending Platform Migration – Phase 2 (Commercial & SME) | Pennant Technologies | Capex | Implementation | 18 | 18 | 15.5 | 18.5 | -0.5 | -2.778% | PO-2025-0481
BFS-LND-001 | Core Lending Platform Migration – Phase 2 (Commercial & SME) | Pennant Technologies | Opex | License & AMC | 6 | 6 | 4.2 | 6 | 0 | 0% | PO-2025-0482
BFS-LND-001 | Core Lending Platform Migration – Phase 2 (Commercial & SME) | In-house | Opex | Resourcing | 4.5 | 4.5 | 3.8 | 4.6 | -0.1 | -2.222% | –
BFS-AI-002 | FinAI – Conversational AI for Sales (BFL 3.0) | In-house | Opex | Resourcing | 5 | 5 | 2.1 | 5 | 0 | 0% | –
BFS-AI-002 | FinAI – Conversational AI for Sales (BFL 3.0) | Nagarro | Capex | Implementation | 4 | 3 | 1.5 | 4 | 0 | 0% | PO-2025-0533
BFS-AI-002 | FinAI – Conversational AI for Sales (BFL 3.0) | AWS | Opex | Cloud Consumption | 2 | 0 | 0.8 | 2 | 0 | 0% | –
BFS-AI-003 | FinAI – Explainable AI for Risk & Underwriting | In-house | Opex | Resourcing | 6 | 6 | 3.6 | 5.9 | 0.1 | 1.667% | –
BFS-AI-003 | FinAI – Explainable AI for Risk & Underwriting | AWS | Opex | Cloud Consumption | 1.5 | 0 | 0.9 | 1.5 | 0 | 0% | –
BFS-AI-004 | FinAI – Copilot/Autopilot in Operations & Service | In-house | Opex | Resourcing | 5.5 | 5.5 | 1.8 | 5.5 | 0 | 0% | –
BFS-AI-004 | FinAI – Copilot/Autopilot in Operations & Service | Nagarro | Capex | Implementation | 3 | 2 | 0.6 | 3.2 | -0.2 | -6.667% | PO-2026-0114
BFS-CLD-005 | Oracle Cloud Infrastructure Migration – Wave 2 | Oracle | Capex | Implementation | 12 | 12 | 8.5 | 15 | -3 | -25% | PO-2025-0501
BFS-CLD-005 | Oracle Cloud Infrastructure Migration – Wave 2 | Oracle | Opex | Cloud Consumption | 8 | 0 | 6.8 | 12 | -4 | -50% | –
BFS-CLD-005 | Oracle Cloud Infrastructure Migration – Wave 2 | In-house | Opex | Resourcing | 3.5 | 3.5 | 2.4 | 3.8 | -0.3 | -8.571% | –
BFS-DCX-006 | Bajaj Finserv Super-App Re-platform | Nagarro | Capex | Implementation | 9 | 9 | 4.2 | 9.6 | -0.6 | -6.667% | PO-2025-0560
BFS-DCX-006 | Bajaj Finserv Super-App Re-platform | In-house | Opex | Resourcing | 3 | 3 | 1.6 | 3.1 | -0.1 | -3.333% | –
BFS-CMP-007 | AML Uplift – Azentio Amlock Upgrade | Azentio | Capex | License & Upgrade | 5 | 5 | 4 | 5 | 0 | 0% | PO-2025-0470
BFS-CMP-007 | AML Uplift – Azentio Amlock Upgrade | In-house | Opex | Resourcing | 2 | 2 | 1.5 | 2 | 0 | 0% | –
BFS-GRN-008 | Green Finance – Solar & EV Financing Onboarding | In-house | Opex | Resourcing | 3 | 1 | 0.4 | 3 | 0 | 0% | –
BFS-GRN-008 | Green Finance – Solar & EV Financing Onboarding | Partner (TBC) | Capex | Integration | 2 | 0 | 0 | 2 | 0 | 0% | –
BFS-DLO-009 | Digital Loan Origination System Upgrade | In-house | Opex | Resourcing | 6 | 6 | 4 | 6.5 | -0.5 | -8.333% | –
BFS-DLO-009 | Digital Loan Origination System Upgrade | Pennant Technologies | Capex | API & Integration | 4 | 4 | 2.5 | 4.4 | -0.4 | -10% | PO-2025-0512
BFS-OBS-010 | Observability Rollout – New Relic APM | New Relic | Opex | License | 2.5 | 2.5 | 2.4 | 2.5 | 0 | 0% | PO-2025-0455
BFS-OBS-010 | Observability Rollout – New Relic APM | In-house | Opex | Resourcing | 1.5 | 1.5 | 1.4 | 1.5 | 0 | 0% | –
BFS-CX-011 | Adobe Experience Cloud – Campaign Personalisation | Adobe | Capex | Implementation | 6 | 6 | 3 | 6 | 0 | 0% | PO-2025-0548
BFS-CX-011 | Adobe Experience Cloud – Campaign Personalisation | In-house | Opex | Resourcing | 2.5 | 2.5 | 1.3 | 2.5 | 0 | 0% | –
BFS-DAT-012 | Customer 360 Data Platform | In-house | Opex | Resourcing | 8 | 8 | 4.5 | 10 | -2 | -25% | –
BFS-DAT-012 | Customer 360 Data Platform | Nagarro | Capex | Implementation | 7 | 7 | 3.8 | 8.4 | -1.4 | -20% | PO-2025-0561
BFS-DAT-012 | Customer 360 Data Platform | AWS | Opex | Cloud Consumption | 2.5 | 0 | 1.4 | 2.9 | -0.4 | -16% | –
| TOTAL — FY2026-27 portfolio |  |  |  | 143 | 123 | 88.5 | 156.4 | -13.4 | -9.371%
Capex = capital expenditure; Opex = operating expenditure. Negative variance (in brackets) = forecast over budget. Illustrative training data — not actual Bajaj Finserv figures.